## Project Planner
Semester project Gantt chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 45 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[5 empty] | Days | 9 | 3 | 20 | 10 | 3 | 20 | 11 | 3 | 20 | 12 | 3 | 20 | 13 | 3 | 20 | 14 | 3 | 20 | 15 | 3 | 20 | 16 | 3 | 20 | 17 | 3 | 20 | 18 | 3 | 20 | 19 | 3 | 20 | 16 | 3 | 20 | 20 | 3 | 20 | 21 | 3 | 20 | 22 | 3 | 20 | 23 | 3 | 20 | 24 | 3 | 20 | 25 | 3 | 20 | 26 | 3 | 20 | 27 | 3 | 20 | 28 | 3 | 20 | 29 | 3 | 20 | 30 | 3 | 20 | 31 | 3 | 20 | 1 | 4 | 20 | 2 | 4 | 20 | 3 | 4 | 20 | 4 | 4 | 20 | 5 | 4 | 20 | 6 | 4 | 20 | 7 | 4 | 20 | 8 | 4 | 20 | 9 | 4 | 20 | 10 | 4 | 20 | 11 | 4 | 20 | 12 | 4 | 20 | 13 | 4 | 20 | 14 | 4 | 20 | 15 | 4 | 20 | 16 | 4 | 20 | 17 | 4 | 20 | 18 | 4 | 20 | 19 | 4 | 20 | 20 | 4 | 20 | 21 | 4 | 20 | 22 | 4 | 20 | 23 | 4 | 20 | 24 | 4 | 20 | 25 | 4 | 20 | 26 | 4 | 20
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150
Create gant chart | 1 | 2 | 1 | 3 | 100%
Create the structure of the report to fit the phases | 2 | 2 | 2 | 1 | 100%
Create a notepad notes.txt file to write keywords to use in report | 1 | 1 | 1 | 1 | 100%
Read Brief description for Semester project tree times | 1 | 2 | 1 | 2 | 100%
Look trough material text and images for the site | 10 | 2 | 9 | 2 | 100%
Look at similar webpages | 13 | 4 | 14 | 0 | 0%
Summerize the report phase in notes.txt file | 19 | 1 | 19 | 2 | 90%
Make a brainstom chart for logo keywords | 22 | 2 | 46 | 0 | 30%
Scetch logo ideas | 24 | 4 | 48 | 0 | 0%
Create color scheme for the site | 24 | 2 | 48 | 0 | 0%
Use content to list potensial pages | 24 | 4 | 0 | 0 | 0%
Group list of potencial pages into categories | 28 | 2 | 0 | 0 | 0%
Scetch rough design for eatch page with mobile version | 30 | 8 | 0 | 0 | 0%
Figure our what material to place where on page, take notes | 38 | 4 | 0 | 0 | 0%
Resize img, find new images if needed | 42 | 4 | 0 | 0 | 0%
Figure out fonts needed and how they will be used | 24 | 3 | 0 | 0 | 0%
Select one of the logo ideas and create the logo | 28 | 6 | 0 | 0 | 0%
Look at site scetches and figure out if there is any common design elements | 38 | 1 | 0 | 0 | 0%
Summerize the Design phase in notes.txt file | 46 | 2 | 0 | 0 | 0%
Create the minimum page elements | 67 | 2 | 0 | 0 | 0%
Set grey placeholder background color and page width | 69 | 2 | 0 | 0 | 0%
Create the basic elements, header/footer | 71 | 2 | 0 | 0 | 0%
Create navbar with working links to eatch page | 71 | 4 | 0 | 0 | 0%
Create code for common components | 75 | 8 | 0 | 0 | 0%
Create grid of eatch page (mobile/desktop) with background color placeholders | 75 | 25 | 0 | 0 | 0%
Do detailed design of eatch element on each page, fill wiht text/images | 100 | 25 | 0 | 0 | 0%
Summerize the HTML/CSS phase in notes.txt file | 125 | 8 | 0 | 0 | 0%
Check all linkes | 125 | 1 | 0 | 0 | 0%
Spellcheck all text | 125 | 2 | 0 | 0 | 0%
WCAG anlyze page | 127 | 1 | 0 | 0 | 0%
Correct WCAG errors | 128 | 4 | 0 | 0 | 0%
Get two users to test the page and give feedback | 132 | 4 | 0 | 0 | 0%
Summerize the Test phase in notes.txt file | 136 | 2 | 0 | 0 | 0%
Read the notes.txt file | 143 | 4 | 0 | 0 | 0%
Write the Report | 147 | 4 | 0 | 0 | 0%